## Sheet1
Task number | Task name | Start date | End date | Duration (days) | Status | Type and Frequency
1 | Create User Interface | 2022-03-09 | 2022-04-22 | 44 | Ongoing | Milestone
1.1 | Implement interactive map | 2022-03-09 | 2022-03-30 | 21 | Ongoing | Standard (one-time)
1.2 | Implement login/logout | 2022-04-06 | 2022-04-13 | 7 | Ongoing | Standard (one-time)
1.3 | Implement ability to add/modify/delete | 2022-03-31 | 2022-04-25 | 25 | Not yet | Standard (one-time)
1.4 | Implement ability to query/report/view | 2022-03-31 | 2022-04-25 | 25 | Not yet | Standard (one-time)
2 | Create database and server | 2022-03-09 | 2022-04-22 | 44 | Ongoing | Milestone
2.1 | Set up new database | 2022-03-09 | 2022-03-30 | 21 | Done | Standard (one-time)
2.2 | Set up net code to link to UI | 2022-03-31 | 2022-04-22 | 22 | Ongoing | Standard (one-time)
2.3 | Set up login/logout management | 2022-04-05 | 2022-04-22 | 17 | Ongoing | Standard (one-time)
3 | Migrate data | 2022-04-22 | 2022-05-14 | 22 | Done | Milestone
3.1 | Clean existing data | 2022-04-22 | 2022-05-03 | 11 | Done | Standard (one-time)
3.2 | Parse data to new database | 2022-05-03 | 2022-05-14 | 11 | Done | Standard (one-time)
4 | Document work and product | 2022-03-09 | 2022-05-24 | 76 | Ongoing | Milestone
4.1 | Create data dictionary | 2022-04-22 | 2022-05-13 | 21 | Not yet | Standard (one-time)
4.2 | Provide weekly presentations | 2022-03-09 | 2022-05-18 | 70 | Ongoing | Recurring, Weekly
4.3 | Revise other documents as needed | 2022-03-09 | 2022-05-24 | 76 | Ongoing | Standard (one-time)
4.4 | Populate GitHub repository | 2022-03-09 | 2022-05-24 | 76 | Ongoing | Standard (one-time)
5 | Slack time | 2022-05-13 | 2022-05-24 | 11 |  | Standard (one-time)
Formulas:
Duration (days) = ROUND(DATEDIF([Start date], [End date], "d"), 0)